## Milestone Tracker
SteerPlan — Lending Program Milestone Tracker
Program: Instant MSME Loan Feature Launch
Phase | Milestone | Owner | Start Date | End Date | Status | Comments
Phase 1 | Loan Application Form Design | Product | 2026-06-01 | 2026-06-05 | ✅ Done | Completed on time
Phase 1 | Loan Eligibility Criteria Defined | Business | 2026-06-01 | 2026-06-04 | ✅ Done | Approved by leadership
Phase 1 | Loan Application API Built | Engineering | 2026-06-05 | 2026-06-10 | 🔄 In Progress | 70% complete
Phase 2 | Aadhaar KYC Integration | Engineering | 2026-06-06 | 2026-06-11 | 🔄 In Progress | Vendor API delay
Phase 2 | PAN KYC Integration | Engineering | 2026-06-06 | 2026-06-11 | 🔄 In Progress | 60% complete
Phase 2 | KYC Status Tracking System | Product | 2026-06-10 | 2026-06-14 | ⏳ To Do | Starts after API
Phase 3 | Credit Scoring Model Defined | Business | 2026-06-08 | 2026-06-12 | 🔄 In Progress | Under review
Phase 3 | Credit Bureau API Integration | Engineering | 2026-06-10 | 2026-06-14 | ⏳ To Do | Dependency on KYC
Phase 3 | Loan Approval Workflow Built | Product | 2026-06-11 | 2026-06-14 | ⏳ To Do | Design pending
Phase 4 | Bank Transfer API Integration | Engineering | 2026-06-12 | 2026-06-18 | ⏳ To Do | Not started
Phase 4 | EMI Repayment Tracker Built | Engineering | 2026-06-14 | 2026-06-20 | ⏳ To Do | Not started
Phase 4 | Repayment Dashboard | Product | 2026-06-18 | 2026-06-24 | ⏳ To Do | Design pending
| Status | Count
| Done | 2
| In Progress | 5
| To Do | 5

## Resource Plan
SteerPlan — Resource Plan
Program: Instant MSME Loan Feature Launch
Team Member | Role | Team | Responsibilities | Availability | Phase Assigned
Priya Sharma | Product Manager | Product | Own product roadmap, approve designs, sign off features | 100% | All Phases
Rahul Mehta | Engineering Lead | Engineering | Tech architecture, API integration, team delivery | 100% | All Phases
Sneha Reddy | Business Analyst | Business | Define eligibility, credit rules, compliance checks | 80% | Phase 1,3
Arjun Kapoor | Frontend Developer | Engineering | Build loan application UI and KYC screens | 100% | Phase 1,2
Divya Krishnan | Backend Developer | Engineering | Build APIs — loan, KYC, credit, disbursal | 100% | Phase 1,2, 3,4
Vikram Nair | Data Engineer | Engineering | Build repayment tracker and ops dashboard | 80% | Phase 4
Anita Joshi | Compliance Officer | Business | KYC compliance, RBI guidelines, risk review | 60% | Phase 2, 3
PM Intern | Program Manager | PM | Track milestones, resolve blockers, reporting | 100% | All Phases
Team | Members
Engineering | 4
Product | 1
Business | 2
PM | 1

## Risk Register
SteerPlan — Program Risk Register
Program: Instant MSME Loan Feature Launch
Risk ID | Risk Description | Category | Probability | Impact | Risk Level | Mitigation Plan | Owner | Status
R001 | Aadhaar API delay from vendor | Technical | High | High | 🔴 Critical | Identify backup KYC vendor immediately | Engineering Lead | Open
R002 | Credit bureau API integration failure | Technical | Medium | High | 🟠 High | Run parallel testing with mock data | Engineering Lead | Open
R003 | KYC compliance rejection by RBI | Compliance | Low | High | 🟠 High | Early review with compliance officer | Compliance Officer | Open
R004 | Sprint delivery delay beyond 14 June | Program | Medium | High | 🟠 High | Daily standups and blocker escalation | PM Intern | Open
R005 | Low loan application conversion rate | Business | Medium | Medium | 🟡 Medium | Simplify application UI and flow | Product Manager | Open
R006 | Overdue repayments exceeding 15% | Financial | Medium | High | 🟠 High | Build early warning repayment system | Business Analyst | In Progress
R007 | Resource unavailability mid sprint | Program | Low | Medium | 🟡 Medium | Cross train team members as backup | Engineering Lead | Open
R008 | Incomplete documentation before launch | Program | Low | High | 🟢 Low | Allocate 1 hour daily for docs | PM Intern | Open
| Risk Level | Count
| Critical | 1
| Hign | 4
| Medium | 2
| Low | 1

## Stakeholder Map
SteerPlan — Stakeholder Map
Program: Instant MSME Loan Feature Launch
Stakeholder | Role | Team | Influence | Interest | Communication Mode | Frequency | Escalation Path
Priya Sharma | Product Manager | Product | High | High | Weekly Sync | Weekly
Rahul Mehta | Engineering Lead | Engineering | High | High | Daily Standup | Daily
Sneha Reddy | Business Analyst | Business | Medium | High | Email UpDate | Weekly
Arjun Kapoor | Frontend Developer | Engineering | Medium | Medium | Sprint Board | Daily
Divya Krishnan | Backend Developer | Engineering | Medium | High | Sprint Board | Daily
Vikram Nair | Data Engineer | Engineering | High | Medium | Email UpDate | Bi - Weekly
Anita Joshi | Compliance Officer | Business | Low | Medium | Sprint Board | Weekly
Leadership | CTO & CEO | Executive | High | Low | Program Report | Monthly

## Dashboard
SteerPlan — Program Dashboard
KPI Section
Total Milestones | Done | In Progress | To Do | Total Risks
12 | 2 | 5 | 5 | 8